## WPR Data
WEEKLY PROGRESS REPORT ¦ Horizon Commercial Tower – Mumbai ¦ Week 05 ¦ 01 Feb-2011 ¦ Baseline: B0
Active Baseline: B0 ¦ Planned completion: 31-Dec-2012
|  |  |  | Contractor: | SteelForm RCC Contractors |  | Report Wk: | Wk 05 of 80 |  | Baseline: | B0 | Prev Wk Actual: | See Wk 04
Act ID | Phase | Activity | Unit | Total Scope | This Wk Qty | Cum. Actual Qty | Cum. Actual % | ★ Cum. Planned % | Variance (%) | Wks Slip | ★ Delay Reason | ★ Critical Path | Baseline Version | Remarks / Next Week Plan
PHASE I
A01 | Phase I | Excavation – Phase I | Cum | 4200 | 420 | 4200 | 100% | 100% | 0% | 0 | No Delay | Y | B0 | Complete.
A02 | Phase I | Raft & Basement 2 – Shuttering | Sqm | 1800 | 306 | 630 | 35% | 37.5% | -2.5% | 0 | No Delay | Y | B0 | Continue as planned.
A03 | Phase I | Raft & Basement 2 – Reinf | MT | 62 | 9.9 | 19.8 | 32% | 37.5% | -5.5% | 3 | No Delay | Y | B0 | Recovery plan required. Target +3.0% next week.
A04 | Phase I | Raft & Basement 2 – Concrete | Cum | 540 | 75.6 | 118.8 | 22% | 25% | -3% | 0 | No Delay | Y | B0 | Continue as planned.
A05 | Phase I | Basement 1 – Shuttering | Sqm | 1800 | 0 | 0 | 0% | 0% | 0% | 0 | No Delay | Y | B0 | Continue as planned.
A06 | Phase I | Basement 1 – Reinforcement | MT | 58 | 0 | 0 | 0% | 0% | 0% | 0 | No Delay | Y | B0 | Continue as planned.
A07 | Phase I | Basement 1 – Concrete | Cum | 520 | 0 | 0 | 0% | 0% | 0% | 0 | No Delay | Y | B0 | Continue as planned.
A08 | Phase I | Basement Waterproofing | Sqm | 3600 | 0 | 0 | 0% | 0% | 0% | 0 | No Delay | Y | B0 | Continue as planned.
PHASE II
A09 | Phase II | Excavation – Phase II | Cum | 2800 | 336 | 560 | 20% | 40% | -20% | 2 | Material Supply – Steel | Y | B0 | Accelerate. Target +24.0% next week.
A10 | Phase II | Raft & Basement 2 – Shuttering | Sqm | 900 | 0 | 0 | 0% | 0% | 0% | 0 | No Delay | Y | B0 | Continue as planned.
A11 | Phase II | Raft & Basement 2 – Concrete | Cum | 260 | 0 | 0 | 0% | 0% | 0% | 0 | No Delay | Y | B0 | Continue as planned.
A12 | Phase II | Basement 1 – Shuttering | Sqm | 900 | 0 | 0 | 0% | 0% | 0% | 0 | No Delay | Y | B0 | Continue as planned.
A13 | Phase II | Basement 1 – Concrete | Cum | 235 | 0 | 0 | 0% | 0% | 0% | 0 | No Delay | Y | B0 | Continue as planned.
PHASE III
A14 | Phase III | Client Handover – Phase III | LS | 1 | 0.3 | 0.3 | 30% | 83.3% | -53.3% | 5 | Client – Zone Handover Pending | Y | B0 | Recovery plan required. Target +8% next week.
A15 | Phase III | Demolition – Existing Struct | LS | 1 | 0 | 0 | 0% | 0% | 0% | 0 | No Delay | Y | B0 | Continue as planned.
A16 | Phase III | Excavation – Phase III | Cum | 6500 | 0 | 0 | 0% | 0% | 0% | 0 | No Delay | Y | B0 | Continue as planned.
A17 | Phase III | Raft – Reinforcement | MT | 130 | 0 | 0 | 0% | 0% | 0% | 0 | No Delay | Y | B0 | Continue as planned.
A18 | Phase III | Raft – Concrete | Cum | 980 | 0 | 0 | 0% | 0% | 0% | 0 | No Delay | Y | B0 | Continue as planned.
SITE
A19 | Site | Bar Bending & Fabrication | MT | 250 | 20 | 70 | 28% | 21.1% | 6.9% | 0 | No Delay | N | B0 | Continue as planned.

## Baseline Register
BASELINE REGISTER ¦ Horizon Commercial Tower, Mumbai
Baseline | Approved Week | Approval Date | Planned End | Reason for Revision | Impact on Milestones | Approved By
B0 | Wk 01 | 03-Jan-2011 | 31-Dec-2012 | Original approved baseline | MS-1: Wk15 ¦ MS-2: Wk20 ¦ MS-3: Wk30 | Client + Pinnacle
★ Active baseline this week: B0 ¦ Planned completion: 31-Dec-2012