## WPR Data
WEEKLY PROGRESS REPORT ¦ Horizon Commercial Tower – Mumbai ¦ Week 09 ¦ 01 Mar-2011 ¦ Baseline: B1
★ BASELINE REVISED THIS WEEK: B0 → B1 ¦ Reason: Client handover delay Phase III + monsoon impact ¦ New completion: 30-Jun-2013 ¦ Approved by: Project Director
|  |  |  | Contractor: | SteelForm RCC Contractors |  | Report Wk: | Wk 09 of 80 |  | Baseline: | B1 | Prev Wk Actual: | See Wk 08
Act ID | Phase | Activity | Unit | Total Scope | This Wk Qty | Cum. Actual Qty | Cum. Actual % | ★ Cum. Planned % | Variance (%) | Wks Slip | ★ Delay Reason | ★ Critical Path | Baseline Version | Remarks / Next Week Plan
PHASE I
A01 | Phase I | Excavation – Phase I | Cum | 4200 | 0 | 4200 | 100% | 78% | 22% | 0 | No Delay | Y | B1 | Complete.
A02 | Phase I | Raft & Basement 2 – Shuttering | Sqm | 1800 | 144 | 1620 | 90% | 68.2% | 21.8% | 0 | No Delay | Y | B1 | Continue as planned.
A03 | Phase I | Raft & Basement 2 – Reinf | MT | 62 | 5 | 53.3 | 86% | 68.2% | 17.8% | 0 | No Delay | Y | B1 | Continue as planned.
A04 | Phase I | Raft & Basement 2 – Concrete | Cum | 540 | 43.2 | 421.2 | 78% | 58.5% | 19.5% | 0 | No Delay | Y | B1 | Continue as planned.
A05 | Phase I | Basement 1 – Shuttering | Sqm | 1800 | 90 | 90 | 5% | 9.8% | -4.8% | 1 | Mumbai Monsoon / Heavy Rain | Y | B1 | Accelerate. Target +9.0% next week.
A06 | Phase I | Basement 1 – Reinforcement | MT | 58 | 2.3 | 2.3 | 4% | 9.8% | -5.8% | 1 | Mumbai Monsoon / Heavy Rain | Y | B1 | Accelerate. Target +10.0% next week.
A07 | Phase I | Basement 1 – Concrete | Cum | 520 | 0 | 0 | 0% | 0% | 0% | 0 | No Delay | Y | B1 | Continue as planned.
A08 | Phase I | Basement Waterproofing | Sqm | 3600 | 72 | 144 | 4% | 0% | 4% | 0 | No Delay | Y | B1 | Continue as planned.
PHASE II
A09 | Phase II | Excavation – Phase II | Cum | 2800 | 224 | 1400 | 50% | 78% | -28% | 6 | Material Supply – Steel | Y | B1 | Recovery plan required. Target +8% next week.
A10 | Phase II | Raft & Basement 2 – Shuttering | Sqm | 900 | 45 | 135 | 15% | 33.5% | -18.5% | 3 | Material Supply – Steel | Y | B1 | Recovery plan required. Target +8% next week.
A11 | Phase II | Raft & Basement 2 – Concrete | Cum | 260 | 13 | 26 | 10% | 22.3% | -12.3% | 2 | Material Supply – Steel | Y | B1 | Accelerate. Target +16.0% next week.
A12 | Phase II | Basement 1 – Shuttering | Sqm | 900 | 0 | 0 | 0% | 0% | 0% | 0 | No Delay | Y | B1 | Continue as planned.
A13 | Phase II | Basement 1 – Concrete | Cum | 235 | 0 | 0 | 0% | 0% | 0% | 0 | No Delay | Y | B1 | Continue as planned.
PHASE III
A14 | Phase III | Client Handover – Phase III | LS | 1 | 0.1 | 0.7 | 70% | 78% | -8% | 9 | Client – Zone Handover Pending | Y | B1 | Recovery plan required. Target +4.0% next week.
A15 | Phase III | Demolition – Existing Struct | LS | 1 | 0.1 | 0.2 | 18% | 78% | -60% | 4 | Client – Zone Handover Pending | Y | B1 | Recovery plan required. Target +8% next week.
A16 | Phase III | Excavation – Phase III | Cum | 6500 | 0 | 0 | 0% | 13% | -13% | 1 | Client – Zone Handover Pending | Y | B1 | Accelerate. Target +17.0% next week.
A17 | Phase III | Raft – Reinforcement | MT | 130 | 0 | 0 | 0% | 0% | 0% | 0 | No Delay | Y | B1 | Continue as planned.
A18 | Phase III | Raft – Concrete | Cum | 980 | 0 | 0 | 0% | 0% | 0% | 0 | No Delay | Y | B1 | Continue as planned.
SITE
A19 | Site | Bar Bending & Fabrication | MT | 250 | 10 | 120 | 48% | 32.8% | 15.2% | 0 | No Delay | N | B1 | Continue as planned.

## Baseline Register
BASELINE REGISTER ¦ Horizon Commercial Tower, Mumbai
Baseline | Approved Week | Approval Date | Planned End | Reason for Revision | Impact on Milestones | Approved By
B0 | Wk 01 | 03-Jan-2011 | 31-Dec-2012 | Original approved baseline | MS-1: Wk15 ¦ MS-2: Wk20 ¦ MS-3: Wk30 | Client + Pinnacle
B1 | Wk 09 | 01-Mar-2011 | 30-Jun-2013 | Client handover delay Phase III + monsoon impact | MS-1: Wk22 ¦ MS-2: Wk28 ¦ MS-3: Wk38 ¦ All milestones extended 7-8 weeks | Project Director
★ Active baseline this week: B1 ¦ Planned completion: 30-Jun-2013