## WPR Data
WEEKLY PROGRESS REPORT ¦ Horizon Commercial Tower – Mumbai ¦ Week 15 ¦ 12 Apr-2011 ¦ Baseline: B1
Active Baseline: B1 ¦ Revised completion: 30-Jun-2013 ¦ Original completion: 31-Dec-2012 ¦ Revised at: Week 9
|  |  |  | Contractor: | SteelForm RCC Contractors |  | Report Wk: | Wk 15 of 80 |  | Baseline: | B1 |  | Prev Wk Actual: | See Wk 14
Act ID | Phase | Activity | Unit | Total Scope | This Wk Qty | Cum. Actual Qty | Cum. Actual % | ★ Cum. Planned % | Variance (%) | Wks Slip | ★ Delay Reason | Responsible Person | ★ Critical Path | Baseline Version | Remarks / Next Week Plan
PHASE I
A01 | Phase I | Excavation – Phase I | Cum | 4200 | 0 | 4200 | 100% | 78% | 22% | 0 | No Delay | Mr.D | Y | B1 | Complete.
A02 | Phase I | Raft & Basement 2 – Shuttering | Sqm | 1800 | 0 | 1800 | 100% | 78% | 22% | 0 | No Delay | Mr.D | Y | B1 | Complete.
A03 | Phase I | Raft & Basement 2 – Reinf | MT | 62 | 0 | 62 | 100% | 78% | 22% | 0 | No Delay | Mr.D | Y | B1 | Complete.
A04 | Phase I | Raft & Basement 2 – Concrete | Cum | 540 | 0 | 540 | 100% | 78% | 22% | 0 | No Delay | Mr.D | Y | B1 | Complete.
A05 | Phase I | Basement 1 – Shuttering | Sqm | 1800 | 144 | 864 | 48% | 68.2% | -20.2% | 7 | Mumbai Monsoon / Heavy Rain | Mr.D | Y | B1 | Recovery plan required. Target +8% next week.
A06 | Phase I | Basement 1 – Reinforcement | MT | 58 | 4.6 | 26.7 | 46% | 68.2% | -22.2% | 7 | Mumbai Monsoon / Heavy Rain | Mr.D | Y | B1 | Recovery plan required. Target +8% next week.
A07 | Phase I | Basement 1 – Concrete | Cum | 520 | 41.6 | 197.6 | 38% | 58.5% | -20.5% | 6 | Mumbai Monsoon / Heavy Rain | Mr.D | Y | B1 | Recovery plan required. Target +8% next week.
A08 | Phase I | Basement Waterproofing | Sqm | 3600 | 144 | 720 | 20% | 34.6% | -14.6% | 3 | Waterproofing Rework – Flooding | Mr. S | Y | B1 | Recovery plan required. Target +7.0% next week.
PHASE II
A09 | Phase II | Excavation – Phase II | Cum | 2800 | 224 | 2464 | 88% | 78% | 10% | 0 | No Delay | Mr.SK | Y | B1 | Continue as planned.
A10 | Phase II | Raft & Basement 2 – Shuttering | Sqm | 900 | 45 | 360 | 40% | 78% | -38% | 9 | Material Supply – Steel | Mr.SK | Y | B1 | Recovery plan required. Target +8% next week.
A11 | Phase II | Raft & Basement 2 – Concrete | Cum | 260 | 13 | 85.8 | 33% | 78% | -45% | 8 | Material Supply – Steel | Mr.SK | Y | B1 | Recovery plan required. Target +8% next week.
A12 | Phase II | Basement 1 – Shuttering | Sqm | 900 | 36 | 144 | 16% | 39% | -23% | 4 | Material Supply – Steel | Mr.SK | Y | B1 | Recovery plan required. Target +8% next week.
A13 | Phase II | Basement 1 – Concrete | Cum | 235 | 7 | 25.9 | 11% | 29.2% | -18.2% | 3 | Material Supply – Steel | Mr.SK | Y | B1 | Recovery plan required. Target +8% next week.
PHASE III
A14 | Phase III | Client Handover – Phase III | LS | 1 | 0 | 1 | 100% | 78% | 22% | 0 | No Delay | Mr.NJ | Y | B1 | Complete.
A15 | Phase III | Demolition – Existing Struct | LS | 1 | 0.1 | 0.5 | 45% | 78% | -33% | 10 | No Delay | Mr.NJ | Y | B1 | Recovery plan required. Target +8% next week.
A16 | Phase III | Excavation – Phase III | Cum | 6500 | 260 | 1300 | 20% | 78% | -58% | 7 | Client – Zone Handover Pending | Mr.NJ | Y | B1 | Recovery plan required. Target +8% next week.
A17 | Phase III | Raft – Reinforcement | MT | 130 | 3.9 | 10.4 | 8% | 33.5% | -25.5% | 3 | Client – Zone Handover Pending | Mr.NJ | Y | B1 | Recovery plan required. Target +8% next week.
A18 | Phase III | Raft – Concrete | Cum | 980 | 29.4 | 49 | 5% | 22.3% | -17.3% | 2 | Client – Zone Handover Pending | Mr.NJ | Y | B1 | Accelerate. Target +21.0% next week.
SITE
A19 | Site | Bar Bending & Fabrication | MT | 250 | 10 | 175 | 70% | 57.5% | 12.5% | 0 | No Delay | Mr.AJ | N | B1 | Continue as planned.

## Baseline Register
BASELINE REGISTER ¦ Horizon Commercial Tower, Mumbai
Baseline | Approved Week | Approval Date | Planned End | Reason for Revision | Impact on Milestones | Approved By
B0 | Wk 01 | 03-Jan-2011 | 31-Dec-2012 | Original approved baseline | MS-1: Wk15 ¦ MS-2: Wk20 ¦ MS-3: Wk30 | Client + Pinnacle
B1 | Wk 09 | 01-Mar-2011 | 30-Jun-2013 | Client handover delay Phase III + monsoon impact | MS-1: Wk22 ¦ MS-2: Wk28 ¦ MS-3: Wk38 ¦ All milestones extended 7-8 weeks | Project Director
★ Active baseline this week: B1 ¦ Planned completion: 30-Jun-2013